## Project Overview
AnalyticsGear AI Sales Pipeline
4-Week Sprint Plan · Jira-Style Project Tracker
Project Information
Project Code | AG-AISP
Project Name | AI-Native Sales Pipeline
Project Lead | Imroz (Founder)
Start Date | Monday, April 20, 2026
Target Go-Live | Sunday, May 17, 2026
Total Duration | 4 weeks / 28 days
Sprints | 4 one-week sprints
Total Story Points | 108 tasks across 6 epics
Daily Time Budget | 4-6 hours/day
Methodology | Agile / Scrum-inspired, solo dev
Epics
Epic Code | Epic Name | Description | Sprint | Tasks | Priority
EP-01 | Foundation & Setup | Project setup, environments, Qdrant, Claude API integration | Sprint 1 | 12 | P0
EP-02 | RAG + Vector Knowledge Base | Embedding pipeline, vector collections, RAG retrieval, knowledge ingestion | Sprint 1 | 15 | P0
EP-03 | MCP Server Layer | 6 MCP servers: CRM, VectorDB, Email, Scraper, Apollo, LinkedIn | Sprint 1-2 | 24 | P0
EP-04 | AI Agents | Prospecting, Outreach, Follow-up, Analytics agents with ReAct pattern | Sprint 2-3 | 28 | P0
EP-05 | Memory & Feedback Loop | Lead memory, pattern memory, self-improvement mechanisms | Sprint 3 | 12 | P1
EP-06 | Production & Go-Live | Deployment, monitoring, email warmup completion, launch | Sprint 4 | 17 | P0
Sprint Summary
Sprint | Dates | Goal | Key Deliverable | Tasks
Sprint 1 | Apr 20 – Apr 26 | Foundation + Knowledge Base + First MCP Server | Working RAG pipeline retrieving company data + blog content. mcp-crm server operational. | 27
Sprint 2 | Apr 27 – May 3 | All MCP Servers + Prospecting Agent Live | All 6 MCP servers running. Prospecting Agent autonomously finding 25 qualified leads/day. | 27
Sprint 3 | May 4 – May 10 | Outreach + Follow-up + Memory | Full multi-channel outreach with RAG personalization. Memory-augmented follow-ups. | 26
Sprint 4 | May 11 – May 17 | Analytics + Production + Go-Live | System live in production. Daily pipeline running. First real outreach sent. | 28
Definition of Done / Success Criteria
✓ All 6 MCP servers running and discoverable
✓ All 4 agents operational and executing daily
✓ Vector DB populated with 200+ company profiles + AnalyticsGear content
✓ RAG retrieval returning relevant context with > 85% relevance
✓ Email domain warmed up and deliverability validated (no blacklists)
✓ First 10 real cold emails sent, tracking active
✓ Daily pipeline running autonomously on schedule via cron/Prefect
✓ Monitoring dashboard showing LLM costs, agent success rate, engagement metrics
✓ Runbook documented for common issues
✓ At least 1 production bug survived + fixed in first 48 hours (proves resilience)

## Sprint Backlog
Sprint Backlog
All 108 tasks across 4 sprints · Jira-style issue tracker
Task ID | Sprint | Day | Date | Epic | Title | Description | Type | Priority | Estimate (hrs) | Status | Acceptance Criteria
AG-001 | 1 | 1 | 2026-04-20 | EP-01 | Initialize git repo & project structure | Create GitHub repo 'sales-pipeline-ai'. Set up directory structure per blueprint (agents/, mcp_servers/, rag/, memory/, feedback/, config/, prompts/). | Task | P0 | 1 | To Do | Repo initialized with README, .gitignore, LICENSE. Full folder structure created.
AG-002 | 1 | 1 | 2026-04-20 | EP-01 | Set up Python 3.12 venv | Install Python 3.12, create virtual environment, configure pyproject.toml with dependency groups (core, mcp, agents, rag). | Task | P0 | 0.5 | To Do | Venv active, pyproject.toml validates, pip install runs clean.
AG-003 | 1 | 1 | 2026-04-20 | EP-01 | Install core dependencies | Install: anthropic, qdrant-client, mcp-sdk, voyageai, gspread, sendgrid, python-dotenv, apscheduler, pydantic, httpx. | Task | P0 | 0.5 | To Do | All packages installed, no conflicts, import smoke test passes.
AG-004 | 1 | 1 | 2026-04-20 | EP-01 | Configure .env and secrets management | Create .env.example and .env. Add API keys: ANTHROPIC_API_KEY, VOYAGE_API_KEY, APOLLO_API_KEY, SENDGRID_API_KEY, GOOGLE_CREDS_PATH. | Task | P0 | 0.5 | To Do | All keys loaded via python-dotenv. Secrets never committed.
AG-005 | 1 | 1 | 2026-04-20 | EP-01 | Set up Docker Compose with Qdrant | Create docker-compose.yml with Qdrant service. Mount volume for persistence. Test container starts. | Task | P0 | 1 | To Do | docker compose up starts Qdrant on :6333. UI accessible at localhost:6333/dashboard.
AG-006 | 1 | 1 | 2026-04-20 | EP-01 | Validate Claude API access | Test Claude API with claude-sonnet-4-6. Verify tool use works. Measure baseline latency and cost. | Task | P0 | 0.5 | To Do | Successful API call, tool use working, costs logged to spreadsheet.
AG-007 | 1 | 2 | 2026-04-21 | EP-02 | Design vector collection schemas | Define 6 collections: company_profiles, prospect_contacts, ag_content, email_history, industry_knowledge, successful_patterns. Decide vector size (1024 for voyage-3). | Design | P0 | 1 | To Do | Schema document created. Collection configs checked into config/collections.yaml.
AG-008 | 1 | 2 | 2026-04-21 | EP-02 | Create all Qdrant collections | Write init_collections.py. Create all 6 collections with proper vector params (COSINE distance, 1024 dims) and payload indexes. | Task | P0 | 1.5 | To Do | All 6 collections visible in Qdrant dashboard. Script idempotent (safe to re-run).
AG-009 | 1 | 2 | 2026-04-21 | EP-02 | Build embedder module | Write rag/embedder.py wrapping Voyage AI. Handle batching, retries, rate limits. Add cost tracking. | Task | P0 | 2 | To Do | embed_text(str) and embed_batch(List[str]) work. Cost logged per call.
AG-010 | 1 | 2 | 2026-04-21 | EP-02 | Build chunker module | Write rag/chunker.py with strategies per content type: structured (company), paragraph (blog), email (one-per-email). | Task | P0 | 1 | To Do | Unit tests pass. Blog chunks respect 200-token size with 50-token overlap.
AG-011 | 1 | 3 | 2026-04-22 | EP-02 | Ingest 50 sample company profiles | Create target_companies.csv with 50 real ICP-matching companies. Run ingestion script to embed and store in company_profiles collection. | Task | P0 | 2 | To Do | 50 companies visible in Qdrant. Metadata (industry, size, tech_stack) properly stored.
AG-012 | 1 | 3 | 2026-04-22 | EP-02 | Ingest AnalyticsGear blog content | Scrape all 6 blog posts from analyticsgear.com/insights. Chunk and embed into ag_content collection. | Task | P0 | 1.5 | To Do | Blog posts chunked correctly. Retrieval by topic returns relevant passages.
AG-013 | 1 | 3 | 2026-04-22 | EP-02 | Ingest industry knowledge base | Create 1-page summaries per target industry (Banking, Retail, Healthcare, SaaS, Manufacturing, Logistics). Embed into industry_knowledge collection. | Task | P1 | 2 | To Do | 6 industry summaries indexed. Search by industry returns correct results.
AG-014 | 1 | 4 | 2026-04-23 | EP-02 | Build retriever module | Write rag/retriever.py. Implement similarity search with metadata filtering. Support multi-collection queries. | Task | P0 | 2 | To Do | retrieve(query, collection, filters, top_k) returns ranked results with scores.
AG-015 | 1 | 4 | 2026-04-23 | EP-02 | Build RAG context builder | Write rag/context_builder.py. Given a prospect, orchestrate retrieval from multiple collections. Build injected-context prompt. | Task | P0 | 2 | To Do | build_context(prospect_id) returns combined context from company + ag_content + patterns.
AG-016 | 1 | 4 | 2026-04-23 | EP-02 | Evaluate retrieval quality | Write 20 test queries with expected results. Measure precision@5 and recall@5. Tune top-K and score thresholds. | Task | P1 | 1.5 | To Do | Precision@5 ≥ 80%. Results documented. Thresholds committed to config.
AG-017 | 1 | 5 | 2026-04-24 | EP-01 | Build Claude client wrapper | Write llm/claude_client.py with tool use support, streaming, retries, cost tracking, and Langfuse tracing hooks. | Task | P0 | 2 | To Do | Client handles tool calls, streaming, errors gracefully. All calls traced.
AG-018 | 1 | 5 | 2026-04-24 | EP-02 | Write first RAG-augmented email prompt | Design prompt template: given prospect + retrieved context, generate personalized email. Test with 5 prospects. | Task | P0 | 2 | To Do | Generated emails reference company-specific details accurately. No hallucinated facts.
AG-019 | 1 | 5 | 2026-04-24 | EP-02 | Validate email quality | Manually review 10 AI-generated emails. Score: relevance, personalization, tone, CTA clarity. Tune prompt based on issues. | QA | P0 | 1 | To Do | 8/10 emails rated 'would send as-is'. Common issues documented and fixed.
AG-020 | 1 | 6 | 2026-04-25 | EP-03 | Set up Google Sheets CRM | Create service account, credentials.json. Create spreadsheet with 3 sheets: Master Leads, Activity Log, Pipeline Dashboard. Apply schema from blueprint Section 7.2. | Task | P0 | 1 | To Do | Sheet accessible via service account. All columns present. Headers formatted.
AG-021 | 1 | 6 | 2026-04-25 | EP-03 | Build mcp-crm server skeleton | Create mcp_servers/mcp_crm/server.py. Implement server lifecycle (initialize, list_tools, call_tool). | Task | P0 | 2 | To Do | MCP server starts via stdio. Tool discovery returns empty list cleanly.
AG-022 | 1 | 6 | 2026-04-25 | EP-03 | Implement CRM tools (read/write/log) | Add tools: read_leads, write_lead, update_status, log_activity, get_pipeline_stats. Include proper JSON schemas. | Task | P0 | 2.5 | To Do | All 5 tools callable. Writes reflected in Google Sheet. Errors return meaningful messages.
AG-023 | 1 | 6 | 2026-04-25 | EP-03 | Test mcp-crm with Claude Desktop | Add server to Claude Desktop config. Manually test each tool. Verify discovery and execution. | QA | P0 | 0.5 | To Do | Claude Desktop successfully calls all 5 tools end-to-end.
AG-024 | 1 | 7 | 2026-04-26 | EP-01 | Sprint 1 review & retrospective | Document what worked, what didn't. Write Sprint 1 summary (learnings blog post draft #1 for later case study). | Documentation | P1 | 1 | To Do | Retro notes written. Blog post outline drafted.
AG-025 | 1 | 7 | 2026-04-26 | EP-01 | Refactor & technical debt cleanup | Address issues from week: rename confusing vars, add missing docstrings, improve error messages. | Refactor | P2 | 2 | To Do | Code passes linting. All public functions have docstrings.
AG-026 | 1 | 7 | 2026-04-26 | EP-06 | Start email domain warmup | Buy 'outreach.analyticsgear.com' domain. Set up SPF/DKIM/DMARC. Begin warmup via Instantly.ai (takes 3 weeks — start NOW). | Task | P0 | 2 | To Do | Domain purchased. DNS records verified. Warmup campaign running (5-10 emails/day).
AG-027 | 1 | 7 | 2026-04-26 | EP-01 | Plan Sprint 2 in detail | Review Sprint 2 backlog. Adjust estimates based on Sprint 1 velocity. Identify dependencies. | Planning | P1 | 1 | To Do | Sprint 2 plan validated. Any scope changes committed.
AG-028 | 2 | 8 | 2026-04-27 | EP-03 | Build mcp-vectordb server | Expose Qdrant as MCP tools: store_embedding, search_similar, get_by_id, update_metadata, delete_vector. | Task | P0 | 2.5 | To Do | All vector ops callable via MCP. Agents can retrieve/store through standard protocol.
AG-029 | 2 | 8 | 2026-04-27 | EP-03 | Set up SendGrid account | Create SendGrid account, verify sender domain (outreach.analyticsgear.com), configure webhooks for opens/clicks/replies. | Task | P0 | 1 | To Do | SendGrid verified. Webhook URL configured. Test email lands in inbox.
AG-030 | 2 | 8 | 2026-04-27 | EP-03 | Build mcp-email server | Implement tools: send_email, get_opens_clicks, check_deliverability, list_replies. Integrate with SendGrid API. | Task | P0 | 3 | To Do | Email send works end-to-end. Tracking events flow into CRM.
AG-031 | 2 | 9 | 2026-04-28 | EP-03 | Build mcp-scraper base server | Create mcp_servers/mcp_scraper/ with MCP skeleton. Add tools framework. | Task | P0 | 1 | To Do | Server starts. Tool registration works.
AG-032 | 2 | 9 | 2026-04-28 | EP-03 | Add job board scraping tool | Implement scrape_job_boards tool: LinkedIn Jobs + Indeed search for data engineering roles. Use Apify for reliability. | Task | P0 | 2.5 | To Do | Tool returns list of companies hiring data roles in last 7 days.
AG-033 | 2 | 9 | 2026-04-28 | EP-03 | Add company enrichment tools | Implement: get_tech_stack (BuiltWith/Wappalyzer), get_company_news (Google News), get_funding (Crunchbase). | Task | P0 | 2 | To Do | Given a domain, returns tech stack, recent news, funding status.
AG-034 | 2 | 10 | 2026-04-29 | EP-03 | Set up Apollo.io account | Create Apollo account (Basic tier $49). Configure ICP filters. Test API access. | Task | P0 | 0.5 | To Do | API key works. ICP search returns expected results.
AG-035 | 2 | 10 | 2026-04-29 | EP-03 | Build mcp-apollo server | Implement tools: search_companies, search_contacts, get_company_details, verify_email. Handle rate limits. | Task | P0 | 3 | To Do | All tools work. Rate limiting graceful. Results properly typed.
AG-036 | 2 | 10 | 2026-04-29 | EP-03 | Test Apollo end-to-end | Search 'CTOs in SaaS, 100-1000 employees, using Snowflake'. Verify 20 qualified results returned. | QA | P0 | 1 | To Do | Returns relevant leads. Emails verified. Metadata complete.
AG-037 | 2 | 11 | 2026-04-30 | EP-03 | Set up LinkedIn automation | Sign up for Phantombuster ($56/mo) or Expandi. Configure LinkedIn account connection (use warm account, 500+ connections). | Task | P0 | 1 | To Do | Phantombuster authenticated. Test connection request works manually.
AG-038 | 2 | 11 | 2026-04-30 | EP-03 | Build mcp-linkedin server | Implement: search_people, send_connection_request, send_message, get_profile, check_connection_status. | Task | P0 | 3 | To Do | All tools work via MCP. Rate limits respected (20 connections/day).
AG-039 | 2 | 11 | 2026-04-30 | EP-03 | Add anti-detection safeguards | Implement human-like delays (random intervals), daily limits, business-hours-only operation. | Task | P1 | 1 | To Do | No rapid-fire actions. Account activity looks human.
AG-040 | 2 | 12 | 2026-05-01 | EP-04 | Build base agent class | Write agents/base_agent.py with ReAct loop: reason → act → observe → repeat. Handle tool calls from MCP. | Task | P0 | 3 | To Do | Agent executes goal with multi-step tool use. Logs each step.
AG-041 | 2 | 12 | 2026-05-01 | EP-04 | Add agent observability | Integrate Langfuse (or local JSON logging). Trace every reasoning step, tool call, and result. | Task | P0 | 1.5 | To Do | Every agent run produces structured trace. Can replay decision process.
AG-042 | 2 | 12 | 2026-05-01 | EP-04 | Add error recovery & retries | Handle: tool failures, LLM errors, rate limits, max-iterations. Graceful degradation. | Task | P0 | 1.5 | To Do | Agent survives injected failures. Stops at max-iterations with clear error.
AG-043 | 2 | 13 | 2026-05-02 | EP-04 | Write Prospecting Agent system prompt | Craft system prompt defining role, ICP, workflow, tools, and output format. Iterate based on initial runs. | Design | P0 | 2 | To Do | Prompt committed to prompts/prospecting.txt. Agent follows workflow correctly.
AG-044 | 2 | 13 | 2026-05-02 | EP-04 | Implement Prospecting Agent | Build agents/prospecting_agent.py extending base agent. Wire up MCP servers: apollo, linkedin, scraper, vectordb, crm. | Task | P0 | 2.5 | To Do | Agent class instantiates. Discovers all expected tools.
AG-045 | 2 | 13 | 2026-05-02 | EP-04 | Implement AI lead scoring | Give agent ability to score 1-100 on 5 dimensions. Store scores in CRM and vector DB metadata. | Task | P0 | 1.5 | To Do | Scores correlate with manual assessment (> 75% agreement on sample of 20).
AG-046 | 2 | 14 | 2026-05-03 | EP-04 | End-to-end Prospecting Agent test | Run agent with goal 'find 25 qualified leads'. Verify outputs, CRM writes, vector DB populations. | QA | P0 | 2 | To Do | 25 leads in CRM. All scored. HOT leads flagged. No duplicates.
AG-047 | 2 | 14 | 2026-05-03 | EP-04 | Tune prospecting workflow | Based on test results, refine prompt, tool usage, scoring criteria. Re-run until quality hits target. | QA | P1 | 1.5 | To Do | Second test run produces higher-quality leads than first.
AG-048 | 2 | 14 | 2026-05-03 | EP-01 | Sprint 2 retro & docs | Write Sprint 2 retro. Draft blog post #2 on 'Building MCP Servers'. | Documentation | P1 | 1 | To Do | Retro notes done. Blog outline ready.
AG-049 | 3 | 15 | 2026-05-04 | EP-04 | Write Outreach Agent system prompt | Design prompt for RAG-powered email generation. Define tone, length, structure, CTA rules. | Design | P0 | 1.5 | To Do | Prompt yields under-120-word emails with specific company references.
AG-050 | 3 | 15 | 2026-05-04 | EP-04 | Implement Outreach Agent | Build agents/outreach_agent.py. Connect to vectordb (for RAG), email, linkedin, crm MCP servers. | Task | P0 | 2.5 | To Do | Agent runs end-to-end. Drafts email using retrieved context.
AG-051 | 3 | 15 | 2026-05-04 | EP-04 | Build email sequence templates | Define HOT (5-email, 14-day) and WARM (3-email, 10-day) sequences in config/sequences.yaml. | Design | P0 | 1.5 | To Do | Sequences loaded by agent. Agent picks correct step based on sequence_step.
AG-052 | 3 | 16 | 2026-05-05 | EP-06 | Verify email deliverability | Test warmup progress via Mail-Tester. Check SPF/DKIM/DMARC. Verify not on blacklists (MXToolbox). | QA | P0 | 1 | To Do | Mail-Tester score ≥ 9/10. No blacklist hits.
AG-053 | 3 | 16 | 2026-05-05 | EP-04 | Integrate Outreach Agent with email | Wire up agent → email generation → send via mcp-email. Add daily limits (max 30/day initially). | Task | P0 | 2 | To Do | Agent sends real email. Tracking IDs logged. Opens/clicks tracked.
AG-054 | 3 | 16 | 2026-05-05 | EP-04 | Add email safety guardrails | Validate: no typos in lead name, no placeholder tokens left, no duplicate sends, allowlist for testing. | Task | P0 | 1.5 | To Do | Safety checks prevent bad sends. Test email with intentional errors is blocked.
AG-055 | 3 | 17 | 2026-05-06 | EP-04 | Build LinkedIn message generation | RAG-augmented connection notes (under 280 chars) and intro DMs. Tone matched to LinkedIn. | Task | P0 | 2 | To Do | Generated messages pass 'sounds human' test. Character limits respected.
AG-056 | 3 | 17 | 2026-05-06 | EP-04 | Integrate Outreach Agent with LinkedIn | Wire to mcp-linkedin. Handle connection flow: view profile → connect → message post-acceptance. | Task | P0 | 2 | To Do | Agent executes full LinkedIn sequence. Statuses tracked in CRM.
AG-057 | 3 | 17 | 2026-05-06 | EP-04 | Multi-channel orchestration | Agent decides channel mix per lead tier: HOT = email + LinkedIn + call-brief. WARM = email + LinkedIn. | Task | P0 | 1.5 | To Do | Agent executes correct channels based on tier. No channel skipped.
AG-058 | 3 | 18 | 2026-05-07 | EP-04 | Build engagement signal tracker | Poll SendGrid webhooks + LinkedIn activity + CRM. Build unified engagement event stream. | Task | P0 | 2 | To Do | All engagement events logged within 5 min of occurrence.
AG-059 | 3 | 18 | 2026-05-07 | EP-04 | Build reply classifier | LLM-based classifier with 6 classes: INTERESTED, OBJECTION, NOT_NOW, NOT_INTERESTED, OUT_OF_OFFICE, WRONG_PERSON. | Task | P0 | 2 | To Do | Classifier achieves > 85% accuracy on labeled test set of 20 replies.
AG-060 | 3 | 18 | 2026-05-07 | EP-04 | Write Follow-up Agent system prompt | Define workflow: monitor → classify → draft response → update CRM → schedule next action. | Design | P0 | 1 | To Do | Prompt complete. Handles all 6 reply classes distinctly.
AG-061 | 3 | 19 | 2026-05-08 | EP-04 | Implement Follow-up Agent | Build agents/followup_agent.py. Wire engagement tracker + classifier + response drafter. | Task | P0 | 2.5 | To Do | Agent processes 10 simulated replies correctly. Drafts appropriate responses.
AG-062 | 3 | 19 | 2026-05-08 | EP-04 | Add human-in-loop for responses | Before sending any auto-reply, flag for human review (email/Slack). Founder approves or edits. | Task | P0 | 1.5 | To Do | Draft replies land in review queue. Nothing sends without explicit approval.
AG-063 | 3 | 19 | 2026-05-08 | EP-04 | Test full response cycle | Simulate: inbound reply → classification → draft → approval → send → CRM update. | QA | P0 | 1 | To Do | Full cycle completes in under 5 minutes for each reply type.
AG-064 | 3 | 20 | 2026-05-09 | EP-05 | Build lead memory | Per-lead interaction history stored in vector DB. Embed every email, reply, LinkedIn message. | Task | P0 | 2 | To Do | get_lead_history(lead_id) returns chronological interactions with context.
AG-065 | 3 | 20 | 2026-05-09 | EP-05 | Build pattern memory | Store successful outreach (got reply / booked meeting) in successful_patterns collection with metadata. | Task | P0 | 1.5 | To Do | Query 'emails that got replies from SaaS CTOs' returns ranked examples.
AG-066 | 3 | 20 | 2026-05-09 | EP-05 | Memory-augment Outreach Agent | Before drafting any follow-up, agent retrieves lead memory + successful patterns + uses as few-shot examples. | Task | P0 | 2 | To Do | Follow-up emails reference prior interactions accurately. No repetition.
AG-067 | 3 | 21 | 2026-05-10 | EP-04 | End-to-end test of 3 agents | Run Prospecting → Outreach → Follow-up in sequence. Verify handoffs and data flow. | QA | P0 | 3 | To Do | Full pipeline runs with 10 leads. All statuses correct at end. No data loss.
AG-068 | 3 | 21 | 2026-05-10 | EP-05 | Bug fixes from integration testing | Address any issues found. Retest. | Bug | P0 | 1.5 | To Do | All critical bugs resolved. Re-test passes.
AG-069 | 3 | 21 | 2026-05-10 | EP-01 | Sprint 3 retro & docs | Write retro. Draft blog post #3 on 'Multi-Agent Systems in Production'. | Documentation | P1 | 1 | To Do | Retro done. Blog outline complete.
AG-070 | 4 | 22 | 2026-05-11 | EP-04 | Build metrics calculator | Compute: leads processed, emails sent, open rate, reply rate, meetings booked, cost per meeting, pipeline value. | Task | P0 | 2 | To Do | Metrics match CRM reality. Updated daily.
AG-071 | 4 | 22 | 2026-05-11 | EP-04 | Write Analytics Agent system prompt | Agent reviews weekly data, identifies trends, generates recommendations with specific A/B test suggestions. | Design | P0 | 1 | To Do | Prompt complete. Produces actionable recommendations.
AG-072 | 4 | 22 | 2026-05-11 | EP-04 | Implement Analytics Agent | Build agents/analytics_agent.py. Scheduled Friday afternoon. Sends report via email to founder. | Task | P0 | 2 | To Do | Weekly report generated. Sent automatically. Founder reads and acts.
AG-073 | 4 | 23 | 2026-05-12 | EP-05 | Build engagement outcome tracker | Track: which emails got replies, which lead profiles converted to meetings, which patterns worked. | Task | P0 | 2 | To Do | Outcome data flowing into feedback system daily.
AG-074 | 4 | 23 | 2026-05-12 | EP-05 | Build pattern analyzer | Weekly job: find commonalities in successful outreach. Auto-tag patterns and store. | Task | P0 | 2 | To Do | After simulated data, correctly identifies top-performing subject lines and CTAs.
AG-075 | 4 | 23 | 2026-05-12 | EP-05 | Implement scoring optimizer | Adjust lead scoring weights based on which lead profiles actually booked meetings. Log changes. | Task | P1 | 1.5 | To Do | Scoring weights change over time based on real data. Changes logged.
AG-076 | 4 | 24 | 2026-05-13 | EP-04 | Build PipelineOrchestrator | Single entry point coordinating daily runs. Schedule: Prospect 6am, Outreach 8am, Follow-up 9am, Summary 6pm. | Task | P0 | 2.5 | To Do | Orchestrator runs full daily cycle. All 4 agents execute in correct order.
AG-077 | 4 | 24 | 2026-05-13 | EP-04 | Add cross-agent error handling | If Prospecting Agent fails, Outreach should still run on existing pipeline. No cascading failures. | Task | P0 | 1.5 | To Do | Injected failure in one agent doesn't break pipeline. Error notification sent.
AG-078 | 4 | 24 | 2026-05-13 | EP-04 | Set up APScheduler / Prefect | Wire orchestrator to scheduler. Test cron-like execution. Handle missed runs gracefully. | Task | P0 | 1.5 | To Do | Pipeline runs automatically at configured times. Missed runs caught up on next cycle.
AG-079 | 4 | 25 | 2026-05-14 | EP-06 | Provision VPS | Set up Hetzner CX22 or DigitalOcean ($10-20/mo). Configure SSH, firewall, fail2ban, basic hardening. | Task | P0 | 1.5 | To Do | VPS accessible. SSH-only auth. Non-root deploy user configured.
AG-080 | 4 | 25 | 2026-05-14 | EP-06 | Dockerize all services | Write Dockerfile for main app. docker-compose with Qdrant + app + Langfuse. Production secrets via env. | Task | P0 | 2 | To Do | docker compose up on VPS runs full stack. Services healthy.
AG-081 | 4 | 25 | 2026-05-14 | EP-06 | Set up Langfuse monitoring | Self-host Langfuse or use cloud. Configure traces for all agent runs and LLM calls. | Task | P0 | 1.5 | To Do | Every agent run visible in Langfuse. Costs, latency, errors tracked.
AG-082 | 4 | 25 | 2026-05-14 | EP-06 | Set up alerting | Email/Slack alerts on: agent failure, LLM errors > threshold, cost spike, no leads processed today. | Task | P0 | 1 | To Do | Test alert fires for each failure mode. Reaches founder within 2 min.
AG-083 | 4 | 26 | 2026-05-15 | EP-06 | Verify email warmup complete | 4 weeks in — should be fully warmed. Verify inbox placement via Mail-Tester and Gmail inbox check. | QA | P0 | 0.5 | To Do | Score ≥ 9/10. Emails land in Primary inbox, not Promotions/Spam.
AG-084 | 4 | 26 | 2026-05-15 | EP-06 | Full pre-launch smoke test | Run complete daily pipeline on staging data. Verify every component: agents, MCP servers, vector DB, email, tracking. | QA | P0 | 3 | To Do | All green. No errors. Metrics match expected.
AG-085 | 4 | 26 | 2026-05-15 | EP-06 | Write operations runbook | Document: how to check pipeline status, diagnose common failures, restart components, view logs, rollback. | Documentation | P0 | 1.5 | To Do | Runbook covers top 10 operational scenarios. Tested with self.
AG-086 | 4 | 27 | 2026-05-16 | EP-06 | Production deployment | Deploy to VPS. Verify all services healthy. Pipeline scheduled but not yet sending. | Task | P0 | 2 | To Do | All services running on VPS. Schedules active. Dry-run mode on.
AG-087 | 4 | 27 | 2026-05-16 | EP-06 | Soft launch with 10 real leads | Disable dry-run. Let agents send real emails + LinkedIn messages to 10 carefully-reviewed leads. | Task | P0 | 3 | To Do | 10 real outreach touches sent. All delivered. Tracking events received.
AG-088 | 4 | 27 | 2026-05-16 | EP-06 | Monitor & fix production issues | Watch logs, metrics, inbox. Fix any production-only issues that surface. | Bug | P0 | 2 | To Do | All issues triaged. P0/P1 resolved before scaling up.
AG-089 | 4 | 28 | 2026-05-17 | EP-06 | Scale to full daily volume | Increase to full ICP targeting: 25 new leads/day, 30-50 emails/day, 20 LinkedIn connections/day. | Task | P0 | 2 | To Do | Pipeline running at target volume. All safety limits holding.
AG-090 | 4 | 28 | 2026-05-17 | EP-06 | Build operations dashboard | Simple dashboard (Streamlit or Langfuse) showing pipeline health, daily stats, cost, error rate. | Task | P1 | 2 | To Do | Dashboard accessible. Updates daily. Founder checks it each morning.
AG-091 | 4 | 28 | 2026-05-17 | EP-06 | GO LIVE announcement + case study kickoff | Post LinkedIn announcement. Start collecting case study metrics. Schedule weekly reviews. | Milestone | P0 | 1 | To Do | Public announcement posted. Metrics baseline captured. Weekly review scheduled.
AG-092 | 4 | 28 | 2026-05-17 | EP-01 | Project retrospective | Full 4-week retro. What went well, what didn't, key learnings. Draft case study outline. | Documentation | P1 | 1.5 | To Do | Retro complete. Case study outline ready to convert into blog posts and sales collateral.

## Daily Schedule
Daily Schedule
Day-by-day breakdown with hours, tasks, and focus areas
Day | Date | Weekday | Sprint | Focus Area | Tasks | Est. Hours
Day 1 | 2026-04-20 | Mon | Sprint 1 | Environment Setup | • AG-001: Initialize git repo & project structure • AG-002: Set up Python 3.12 venv • AG-003: Install core dependencies • AG-004: Configure .env and secrets management • AG-005: Set up Docker Compose with Qdrant • AG-006: Validate Claude API access | 4.0 hrs
Day 2 | 2026-04-21 | Tue | Sprint 1 | Vector DB Foundation | • AG-007: Design vector collection schemas • AG-008: Create all Qdrant collections • AG-009: Build embedder module • AG-010: Build chunker module | 5.5 hrs
Day 3 | 2026-04-22 | Wed | Sprint 1 | Embedding Pipeline | • AG-011: Ingest 50 sample company profiles • AG-012: Ingest AnalyticsGear blog content • AG-013: Ingest industry knowledge base | 5.5 hrs
Day 4 | 2026-04-23 | Thu | Sprint 1 | RAG Retrieval | • AG-014: Build retriever module • AG-015: Build RAG context builder • AG-016: Evaluate retrieval quality | 5.5 hrs
Day 5 | 2026-04-24 | Fri | Sprint 1 | Claude Integration | • AG-017: Build Claude client wrapper • AG-018: Write first RAG-augmented email prompt • AG-019: Validate email quality | 5.0 hrs
Day 6 | 2026-04-25 | Sat | Sprint 1 | First MCP Server (CRM) | • AG-020: Set up Google Sheets CRM • AG-021: Build mcp-crm server skeleton • AG-022: Implement CRM tools (read/write/log) • AG-023: Test mcp-crm with Claude Desktop | 6.0 hrs
Day 7 | 2026-04-26 | Sun | Sprint 1 | Sprint 1 Review + Start Email Warmup | • AG-024: Sprint 1 review & retrospective • AG-025: Refactor & technical debt cleanup • AG-026: Start email domain warmup • AG-027: Plan Sprint 2 in detail | 6.0 hrs
Day 8 | 2026-04-27 | Mon | Sprint 2 | MCP VectorDB + Email | • AG-028: Build mcp-vectordb server • AG-029: Set up SendGrid account • AG-030: Build mcp-email server | 6.5 hrs
Day 9 | 2026-04-28 | Tue | Sprint 2 | MCP Scraper | • AG-031: Build mcp-scraper base server • AG-032: Add job board scraping tool • AG-033: Add company enrichment tools | 5.5 hrs
Day 10 | 2026-04-29 | Wed | Sprint 2 | MCP Apollo | • AG-034: Set up Apollo.io account • AG-035: Build mcp-apollo server • AG-036: Test Apollo end-to-end | 4.5 hrs
Day 11 | 2026-04-30 | Thu | Sprint 2 | MCP LinkedIn | • AG-037: Set up LinkedIn automation • AG-038: Build mcp-linkedin server • AG-039: Add anti-detection safeguards | 5.0 hrs
Day 12 | 2026-05-01 | Fri | Sprint 2 | Base Agent Architecture | • AG-040: Build base agent class • AG-041: Add agent observability • AG-042: Add error recovery & retries | 6.0 hrs
Day 13 | 2026-05-02 | Sat | Sprint 2 | Prospecting Agent | • AG-043: Write Prospecting Agent system prompt • AG-044: Implement Prospecting Agent • AG-045: Implement AI lead scoring | 6.0 hrs
Day 14 | 2026-05-03 | Sun | Sprint 2 | Sprint 2 Review | • AG-046: End-to-end Prospecting Agent test • AG-047: Tune prospecting workflow • AG-048: Sprint 2 retro & docs | 4.5 hrs
Day 15 | 2026-05-04 | Mon | Sprint 3 | Outreach Agent Foundation | • AG-049: Write Outreach Agent system prompt • AG-050: Implement Outreach Agent • AG-051: Build email sequence templates | 5.5 hrs
Day 16 | 2026-05-05 | Tue | Sprint 3 | Email Channel Integration | • AG-052: Verify email deliverability • AG-053: Integrate Outreach Agent with email • AG-054: Add email safety guardrails | 4.5 hrs
Day 17 | 2026-05-06 | Wed | Sprint 3 | LinkedIn Channel Integration | • AG-055: Build LinkedIn message generation • AG-056: Integrate Outreach Agent with LinkedIn • AG-057: Multi-channel orchestration | 5.5 hrs
Day 18 | 2026-05-07 | Thu | Sprint 3 | Follow-up Agent | • AG-058: Build engagement signal tracker • AG-059: Build reply classifier • AG-060: Write Follow-up Agent system prompt | 5.0 hrs
Day 19 | 2026-05-08 | Fri | Sprint 3 | Reply Handling | • AG-061: Implement Follow-up Agent • AG-062: Add human-in-loop for responses • AG-063: Test full response cycle | 5.0 hrs
Day 20 | 2026-05-09 | Sat | Sprint 3 | Memory System | • AG-064: Build lead memory • AG-065: Build pattern memory • AG-066: Memory-augment Outreach Agent | 5.5 hrs
Day 21 | 2026-05-10 | Sun | Sprint 3 | Sprint 3 Review | • AG-067: End-to-end test of 3 agents • AG-068: Bug fixes from integration testing • AG-069: Sprint 3 retro & docs | 5.5 hrs
Day 22 | 2026-05-11 | Mon | Sprint 4 | Analytics Agent | • AG-070: Build metrics calculator • AG-071: Write Analytics Agent system prompt • AG-072: Implement Analytics Agent | 5.0 hrs
Day 23 | 2026-05-12 | Tue | Sprint 4 | Feedback Loop | • AG-073: Build engagement outcome tracker • AG-074: Build pattern analyzer • AG-075: Implement scoring optimizer | 5.5 hrs
Day 24 | 2026-05-13 | Wed | Sprint 4 | Orchestrator | • AG-076: Build PipelineOrchestrator • AG-077: Add cross-agent error handling • AG-078: Set up APScheduler / Prefect | 5.5 hrs
Day 25 | 2026-05-14 | Thu | Sprint 4 | Production Setup | • AG-079: Provision VPS • AG-080: Dockerize all services • AG-081: Set up Langfuse monitoring • AG-082: Set up alerting | 6.0 hrs
Day 26 | 2026-05-15 | Fri | Sprint 4 | Final Checks | • AG-083: Verify email warmup complete • AG-084: Full pre-launch smoke test • AG-085: Write operations runbook | 5.0 hrs
Day 27 | 2026-05-16 | Sat | Sprint 4 | Soft Launch | • AG-086: Production deployment • AG-087: Soft launch with 10 real leads • AG-088: Monitor & fix production issues | 7.0 hrs
Day 28 | 2026-05-17 | Sun | Sprint 4 | GO LIVE 🚀 | • AG-089: Scale to full daily volume • AG-090: Build operations dashboard • AG-091: GO LIVE announcement + case study kickoff • AG-092: Project retrospective | 6.5 hrs

## Kanban Board
Kanban Board
Backlog → To Do → In Progress → Review → Done
📋 Backlog | 🟡 To Do (Current Sprint) | 🟠 In Progress | 🔵 Review | ✅ Done
AG-028 [S2] Build mcp-vectordb server... P0 • 2.5h | AG-001 Initialize git repo & project structure Priority: P0 • 1h
AG-029 [S2] Set up SendGrid account... P0 • 1h | AG-002 Set up Python 3.12 venv Priority: P0 • 0.5h
AG-030 [S2] Build mcp-email server... P0 • 3h | AG-003 Install core dependencies Priority: P0 • 0.5h
AG-031 [S2] Build mcp-scraper base server... P0 • 1h | AG-004 Configure .env and secrets management Priority: P0 • 0.5h
AG-032 [S2] Add job board scraping tool... P0 • 2.5h | AG-005 Set up Docker Compose with Qdrant Priority: P0 • 1h
AG-033 [S2] Add company enrichment tools... P0 • 2h | AG-006 Validate Claude API access Priority: P0 • 0.5h
AG-034 [S2] Set up Apollo.io account... P0 • 0.5h | AG-007 Design vector collection schemas Priority: P0 • 1h
AG-035 [S2] Build mcp-apollo server... P0 • 3h | AG-008 Create all Qdrant collections Priority: P0 • 1.5h
AG-036 [S2] Test Apollo end-to-end... P0 • 1h | AG-009 Build embedder module Priority: P0 • 2h
AG-037 [S2] Set up LinkedIn automation... P0 • 1h | AG-010 Build chunker module Priority: P0 • 1h
AG-038 [S2] Build mcp-linkedin server... P0 • 3h | AG-011 Ingest 50 sample company profiles Priority: P0 • 2h
AG-039 [S2] Add anti-detection safeguards... P1 • 1h | AG-012 Ingest AnalyticsGear blog content Priority: P0 • 1.5h
AG-040 [S2] Build base agent class... P0 • 3h | AG-013 Ingest industry knowledge base Priority: P1 • 2h
AG-041 [S2] Add agent observability... P0 • 1.5h | AG-014 Build retriever module Priority: P0 • 2h
AG-042 [S2] Add error recovery & retries... P0 • 1.5h | AG-015 Build RAG context builder Priority: P0 • 2h
AG-043 [S2] Write Prospecting Agent system prompt... P0 • 2h | AG-016 Evaluate retrieval quality Priority: P1 • 1.5h
AG-044 [S2] Implement Prospecting Agent... P0 • 2.5h | AG-017 Build Claude client wrapper Priority: P0 • 2h
AG-045 [S2] Implement AI lead scoring... P0 • 1.5h | AG-018 Write first RAG-augmented email prompt Priority: P0 • 2h
AG-046 [S2] End-to-end Prospecting Agent test... P0 • 2h | AG-019 Validate email quality Priority: P0 • 1h
AG-047 [S2] Tune prospecting workflow... P1 • 1.5h | AG-020 Set up Google Sheets CRM Priority: P0 • 1h
AG-048 [S2] Sprint 2 retro & docs... P1 • 1h | AG-021 Build mcp-crm server skeleton Priority: P0 • 2h
AG-049 [S3] Write Outreach Agent system prompt... P0 • 1.5h | AG-022 Implement CRM tools (read/write/log) Priority: P0 • 2.5h
AG-050 [S3] Implement Outreach Agent... P0 • 2.5h | AG-023 Test mcp-crm with Claude Desktop Priority: P0 • 0.5h
AG-051 [S3] Build email sequence templates... P0 • 1.5h | AG-024 Sprint 1 review & retrospective Priority: P1 • 1h
AG-052 [S3] Verify email deliverability... P0 • 1h | AG-025 Refactor & technical debt cleanup Priority: P2 • 2h
💡 Move cards between columns as work progresses. The Sprint Backlog sheet is the source of truth for all tasks.

## Milestones
Project Milestones
Key checkpoints with deliverables and success criteria
Milestone | Target Date | Day | Deliverable | Success Criteria
M1 — Foundation Complete | 2026-04-24 | Day 5 | Working RAG pipeline with embedding, retrieval, and Claude integration | Can generate a personalized email using retrieved company + blog context. Quality rated 8/10.
M2 — First MCP Server Live | 2026-04-25 | Day 6 | mcp-crm server operational and tested with Claude Desktop | Claude Desktop can read/write CRM via MCP. Tool discovery works.
M3 — All MCP Servers Operational | 2026-05-01 | Day 12 | 6 MCP servers: crm, vectordb, email, scraper, apollo, linkedin | All servers run, all tools discoverable, all pass integration tests.
M4 — Prospecting Agent Live | 2026-05-03 | Day 14 | Autonomous agent finding 25 qualified leads/day | Agent runs end-to-end without human intervention. 25 leads scored and stored.
M5 — Full Multi-Agent System | 2026-05-10 | Day 21 | Prospecting + Outreach + Follow-up agents integrated | Full pipeline runs with 10 test leads. All statuses correctly updated.
M6 — Production Deployed | 2026-05-14 | Day 25 | System running on VPS with monitoring and scheduling | Services healthy. Scheduled runs execute. Alerts fire on failure.
M7 — Soft Launch | 2026-05-16 | Day 27 | First 10 real outreach messages sent | Real emails delivered. Tracking events received. Any P0 bugs fixed.
M8 — GO LIVE 🚀 | 2026-05-17 | Day 28 | Full production volume — daily pipeline running autonomously | 25 leads/day, 30-50 emails/day, 20 LinkedIn connections/day. Dashboard live.

## Dependencies
Dependencies & Critical Path
Task dependencies and blocking relationships
Task | Depends On | Blocks | Critical Path?
AG-007 (Vector collections) | AG-005 (Qdrant running) | AG-008, AG-011, AG-012, AG-013 | YES
AG-009 (Embedder) | AG-003 (Voyage installed) | AG-011, AG-012, AG-013, AG-014 | YES
AG-014 (Retriever) | AG-009, AG-011, AG-012 | AG-015, AG-018 | YES
AG-018 (RAG email prompt) | AG-014, AG-017 (Claude client) | AG-049, AG-050 (Outreach Agent) | YES
AG-026 (Email warmup) | None — START DAY 7 | AG-052, AG-083 (deliverability, go-live) | YES (3-week critical path)
AG-028-AG-038 (All MCP servers) | AG-006 (Claude API) | AG-040, AG-044 (Agents) | YES
AG-040 (Base agent) | AG-017, MCP servers running | AG-044, AG-050, AG-061, AG-072 | YES
AG-044 (Prospecting Agent) | AG-040, mcp-apollo, mcp-linkedin, mcp-vectordb, mcp-crm | AG-046 (Sprint 2 goal) | YES
AG-050 (Outreach Agent) | AG-044, mcp-email, AG-018 (RAG) | AG-061 (Follow-up), AG-067 (E2E test) | YES
AG-061 (Follow-up Agent) | AG-059 (Classifier), AG-058 (Signal tracker) | AG-067 (E2E test) | YES
AG-064-AG-066 (Memory) | AG-050 (Outreach sending emails) | AG-073 (feedback), quality improvement | Medium
AG-076 (Orchestrator) | All 4 agents operational | AG-086 (Prod deploy) | YES
AG-079 (VPS) | None — can run in parallel | AG-080, AG-086 (deploy) | YES
AG-086 (Production deploy) | AG-076, AG-080, AG-081, AG-082 | AG-087, AG-089 (launch) | YES
AG-083 (Warmup complete) | AG-026 (started Day 7 = 4 weeks prior) | AG-087 (real email sends) | YES
AG-089 (Scale to full volume) | AG-087 (soft launch successful) | 🚀 GO LIVE | YES

## Risk Register
Risk Register
Known risks with mitigation plans
Risk ID | Risk | Likelihood | Impact | Mitigation | Owner
R-01 | Email domain gets blacklisted during warmup | Medium | HIGH | Use separate domain from analyticsgear.com. Warm up slowly (5/day → 50/day over 3 weeks). Monitor MXToolbox weekly. | Founder
R-02 | LinkedIn account gets restricted due to automation | High | HIGH | Strict 20-connections/day limit. Human-like delays. Business-hours only. Have backup account ready. | Founder
R-03 | MCP tool calls fail at scale (API rate limits) | Medium | Medium | Implement exponential backoff. Cache responses where possible. Set per-API daily caps. Monitor in Langfuse. | Founder
R-04 | LLM costs spike unexpectedly | Medium | Medium | Set monthly budget alerts in Anthropic console. Use Haiku for cheap tasks (scoring). Cache RAG context where possible. | Founder
R-05 | RAG retrieval quality too low (irrelevant results) | Medium | HIGH | Evaluate retrieval in Day 4 (AG-016). Tune chunking, embedding model, top-K. Add re-ranker if needed. | Founder
R-06 | Agents hallucinate facts about prospects | High | HIGH | Agent system prompts explicitly say 'only use facts from retrieved context'. Human review for first 2 weeks of outreach. | Founder
R-07 | Timeline slips due to complexity | Medium | Medium | Buffer built into weekends. P2 tasks droppable. Keep scope — no feature creep. Weekly retros to catch early. | Founder
R-08 | Single point of failure (founder sick / traveling) | Low | HIGH | Document everything as you build. Runbook on Day 26. Monitoring alerts ensure failures surface even if unattended. | Founder
R-09 | Apollo/LinkedIn API changes break scrapers | Medium | Medium | MCP abstraction isolates changes. Pay for legitimate APIs where possible. Have fallback: manual CSV import. | Founder
R-10 | Real prospects complain about automated outreach | Low | HIGH | Easy unsubscribe in every email. Honor GDPR/CAN-SPAM. Human approval for first 100 emails. Legitimate personalization (not spam). | Founder

## Progress Tracker
Progress Tracker
Daily progress log — update as you go
Day | Date | Planned Tasks | Completed | Blocked/Issues | Tomorrow's Priority | Hours Spent
Day 1 | 2026-04-20 | 6
Day 2 | 2026-04-21 | 4
Day 3 | 2026-04-22 | 3
Day 4 | 2026-04-23 | 3
Day 5 | 2026-04-24 | 3
Day 6 | 2026-04-25 | 4
Day 7 | 2026-04-26 | 4
Day 8 | 2026-04-27 | 3
Day 9 | 2026-04-28 | 3
Day 10 | 2026-04-29 | 3
Day 11 | 2026-04-30 | 3
Day 12 | 2026-05-01 | 3
Day 13 | 2026-05-02 | 3
Day 14 | 2026-05-03 | 3
Day 15 | 2026-05-04 | 3
Day 16 | 2026-05-05 | 3
Day 17 | 2026-05-06 | 3
Day 18 | 2026-05-07 | 3
Day 19 | 2026-05-08 | 3
Day 20 | 2026-05-09 | 3
Day 21 | 2026-05-10 | 3
Day 22 | 2026-05-11 | 3
Day 23 | 2026-05-12 | 3
Day 24 | 2026-05-13 | 3
Day 25 | 2026-05-14 | 4
Day 26 | 2026-05-15 | 3
Day 27 | 2026-05-16 | 3
Day 28 | 2026-05-17 | 4
💡 Fill in 'Completed', 'Blocked/Issues', and 'Tomorrow's Priority' at end of each day. Use as a daily standup log.